## Project tasks
Project name | Cloud Kitchen
Project manager | Amit Sharma
Project start date | 2022-11-13 09:00
Project finish date | 2023-06-12 17:00
Duration | 151 days
% complete | 0%
Exported on | 2022-11-27 05:46
Task number | Outline number | Phase and Name | Assigned to | Duration | Start | Finish | Depends on | % complete | Bucket | Dependents (after) | Effort | Effort completed | Effort remaining | Milestone | Notes | Labels | Priority | Sprint
1 | 1 | Initiation |  | 1.63 days | 2022-11-14 09:00 | 2022-11-15 14:00 |  | 0% |  |  | 20 hours | 0 hours | 20 hours | No |  |  | Medium
2 | 1.1 | Determine project scope | Project Manager | 4 hours | 2022-11-14 09:00 | 2022-11-14 13:00 |  | 0% | Scope | 3 - Business Proposal Document | 4 hours | 0 hours | 4 hours | No |  | Project Manager | Medium | Backlog
3 | 1.2 | Business Proposal Document | Project Manager | 1 day | 2022-11-14 13:00 | 2022-11-15 13:00 | 2 - Determine project scope | 0% | Scope |  | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
4 | 1.3 | Project Charter | Project Manager | 1 day | 2022-11-14 14:00 | 2022-11-15 14:00 |  | 0% | Scope | 8 - Secure core resources | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
5 | 2 | Analysis/Software Requirements |  | 8.38 days | 2022-11-15 14:00 | 2022-11-25 17:00 |  | 0% |  |  | 144 hours | 0 hours | 144 hours | No |  |  | Medium
6 | 2.1 | Conduct needs analysis | Business Analysis Team | 5 days | 2022-11-15 14:00 | 2022-11-22 14:00 |  | 0% | Analysis/Software Requirements | 7 - Review software specifications/budget with team | 40 hours | 0 hours | 40 hours | No |  | Project Manager | Medium | Backlog
7 | 2.2 | Review software specifications/budget with team | Business Analysis Team | 4 hours | 2022-11-22 14:00 | 2022-11-23 10:00 | 6 - Conduct needs analysis | 0% | Analysis/Software Requirements |  | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
8 | 2.3 | Secure core resources | Business Analysis Team | 1 day | 2022-11-16 14:00 | 2022-11-17 14:00 | 4 - Project Charter | 0% | Scope | 9 - Develop delivery timeline | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
9 | 2.4 | Develop delivery timeline | Business Analysis Team | 1 day | 2022-11-17 14:00 | 2022-11-18 14:00 | 8 - Secure core resources | 0% | Analysis/Software Requirements |  | 8 hours | 0 hours | 8 hours | No |  | Development Team;Project Manager | Medium | Backlog
10 | 2.5 | Design |  | 8 days | 2022-11-16 09:00 | 2022-11-25 17:00 |  | 0% |  |  | 80 hours | 0 hours | 80 hours | No |  |  | Medium
11 | 2.5.1 | Develop functional specifications | Business Analysis Team | 5 days | 2022-11-16 09:00 | 2022-11-22 17:00 |  | 0% | Design |  | 40 hours | 0 hours | 40 hours | No |  | Project Manager | Medium | Backlog
12 | 2.5.2 | Develop prototype based on functional specifications | Business Analysis Team | 4 days | 2022-11-21 09:00 | 2022-11-24 17:00 |  | 0% | Design |  | 32 hours | 0 hours | 32 hours | No | Bu siness Team | Design Team | Medium | Backlog
13 | 2.5.3 | Conduct user testing | Business Analysis Team | 5 days | 2022-11-21 09:00 | 2022-11-25 17:00 |  | 0% | Design |  |  |  |  | No |  | Design Team | Medium | Backlog
14 | 2.5.4 | Obtain approval to proceed | Business Analysis Team | 16 hours | 2022-11-24 09:00 | 2022-11-25 17:00 |  | 0% | Design |  | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
15 | 3 | Development |  | 95 days | 2022-11-28 09:00 | 2023-04-07 17:00 |  | 0% |  |  | 192 hours | 0 hours | 192 hours | No |  |  | Medium
16 | 3.1 | Identify modular/tiered design parameters | Development Team | 12 days | 2022-11-28 09:00 | 2022-12-13 17:00 |  | 0% | Development |  | 8 hours | 0 hours | 8 hours | No |  | Development Team | Medium | Backlog
17 | 3.2 | Assign development staff | Development Team | 1 day | 2022-12-12 09:00 | 2022-12-12 17:00 |  | 0% | Development | 18 - Develop code | 8 hours | 0 hours | 8 hours | No |  | Development Team | Medium | Backlog
18 | 3.3 | Develop code | Development Team | 53 days | 2022-12-13 09:00 | 2023-02-23 17:00 | 17 - Assign development staff | 0% | Development | 32 - Develop user manuals | 120 hours | 0 hours | 120 hours | No |  | Development Team | Medium | Backlog
19 | 3.4 | Testing |  | 30 days | 2023-02-27 09:00 | 2023-04-07 17:00 |  | 0% |  |  | 56 hours | 0 hours | 56 hours | No |  |  | Medium
20 | 3.4.1 | Unit Testing |  | 5 days | 2023-02-27 09:00 | 2023-03-03 17:00 |  | 0% |  |  | 24 hours | 0 hours | 24 hours | No |  |  | Medium
21 | 3.4.1.1 | Identify anomalies to product specifications | Development Team | 5 days | 2023-02-27 09:00 | 2023-03-03 17:00 |  | 0% | Testing |  | 24 hours | 0 hours | 24 hours | No |  | Quality Assurance Team | Medium | Backlog
22 | 3.4.1.2 | Unit testing complete | Development Team | 0 days | 2023-03-03 09:00 | 2023-03-03 09:00 |  | 0% | Testing |  |  |  |  | Yes |  | Quality Assurance Team | Medium | Backlog
23 | 3.4.2 | Integration Testing |  | 25 days | 2023-03-06 09:00 | 2023-04-07 17:00 |  | 0% |  |  | 32 hours | 0 hours | 32 hours | No |  |  | Medium
24 | 3.4.2.1 | Identify anomalies to specifications | QA Team | 16 days | 2023-03-06 09:00 | 2023-03-27 17:00 |  | 0% | Testing |  | 16 hours | 0 hours | 16 hours | No |  | Quality Assurance Team | Medium | Backlog
25 | 3.4.2.2 | Re-test modified code | QA Team | 9 days | 2023-03-28 09:00 | 2023-04-07 17:00 |  | 0% | Testing |  | 16 hours | 0 hours | 16 hours | No |  | Quality Assurance Team | Medium | Backlog
26 | 4 | Post Development |  | 43 days | 2023-04-06 09:00 | 2023-06-05 17:00 |  | 0% |  |  | 360 hours | 0 hours | 360 hours | No |  |  | Medium
27 | 4.1 | Identify training delivery methodology (computer based training, classroom, etc.) | Dev, QA, Content Team | 2 days | 2023-04-06 09:00 | 2023-04-07 17:00 |  | 0% | Training | 28 - Develop training materials | 16 hours | 0 hours | 16 hours | No |  | Content Team | Medium | Backlog
28 | 4.2 | Develop training materials | Dev, QA, Content Team | 4 weeks | 2023-04-10 09:00 | 2023-05-05 17:00 | 27 - Identify training delivery methodology (computer based training, classroom, etc.) | 0% | Training |  | 120 hours | 0 hours | 120 hours | No |  | Content Team | Medium | Backlog
29 | 4.3 | Develop training delivery mechanism | Dev, QA, Content Team | 4 days | 2023-05-08 09:00 | 2023-05-11 17:00 |  | 0% | Training |  | 16 hours | 0 hours | 16 hours | No |  | Content Team | Medium | Backlog
30 | 4.4 | Documentation |  | 7 days | 2023-05-15 10:00 | 2023-05-24 10:00 |  | 0% |  |  | 144 hours | 0 hours | 144 hours | No |  |  | Medium
31 | 4.4.1 | Develop Help specification | Dev, QA, Content Team | 1 day | 2023-05-15 10:00 | 2023-05-16 10:00 |  | 0% | Documentation |  | 8 hours | 0 hours | 8 hours | No |  | Content Team | Medium | Backlog
32 | 4.4.2 | Develop user manuals | Dev, QA, Content Team | 1 week | 2023-05-15 10:00 | 2023-05-22 10:00 | 18 - Develop code | 0% | Documentation | 33 - Review all user documentation | 120 hours | 0 hours | 120 hours | No |  | Content Team | Medium | Backlog
33 | 4.4.3 | Review all user documentation | Dev, QA, Content Team | 2 days | 2023-05-22 10:00 | 2023-05-24 10:00 | 32 - Develop user manuals | 0% | Documentation |  | 16 hours | 0 hours | 16 hours | No |  | Content Team | Medium | Backlog
34 | 4.5 | Pilot |  | 8 days | 2023-05-25 09:00 | 2023-06-05 17:00 |  | 0% |  |  | 64 hours | 0 hours | 64 hours | No |  |  | Medium
35 | 4.5.1 | Identify test group | Dev, QA, Content Team | 1 day | 2023-05-25 09:00 | 2023-05-25 17:00 |  | 0% | Pilot |  | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
36 | 4.5.2 | Install/deploy software | Dev, QA, Content Team | 1 day | 2023-05-26 09:00 | 2023-05-26 17:00 |  | 0% | Pilot | 37 - Obtain user feedback | 8 hours | 0 hours | 8 hours | No |  | Development Team | Medium | Backlog
37 | 4.5.3 | Obtain user feedback | Dev, QA, Content Team | 1 week | 2023-05-29 09:00 | 2023-06-02 17:00 | 36 - Install/deploy software | 0% | Pilot | 38 - Evaluate testing information | 40 hours | 0 hours | 40 hours | No |  | Project Manager | Medium | Backlog
38 | 4.5.4 | Evaluate testing information | Dev, QA, Content Team | 1 day | 2023-06-05 09:00 | 2023-06-05 17:00 | 37 - Obtain user feedback | 0% | Pilot |  | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
39 | 5 | Deployment |  | 6 days | 2023-06-05 09:00 | 2023-06-12 17:00 |  | 0% |  |  | 48 hours | 0 hours | 48 hours | No |  |  | Medium
40 | 5.1 | Secure deployment resources | System Team | 1 day | 2023-06-05 09:00 | 2023-06-05 17:00 |  | 0% | Deployment | 41 - Train support staff | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
41 | 5.2 | Train support staff | System Team | 1 day | 2023-06-06 09:00 | 2023-06-06 17:00 | 40 - Secure deployment resources | 0% | Deployment | 42 - Deploy software | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
42 | 5.3 | Deploy software | System Team | 1 day | 2023-06-07 09:00 | 2023-06-07 17:00 | 41 - Train support staff | 0% | Deployment | 44 - Document lessons learned | 8 hours | 0 hours | 8 hours | No |  | Development Team | Medium | Backlog
43 | 5.4 | Post Deployment |  | 3 days | 2023-06-08 09:00 | 2023-06-12 17:00 |  | 0% |  |  | 24 hours | 0 hours | 24 hours | No |  |  | Medium
44 | 5.4.1 | Document lessons learned | Project Manager | 1 day | 2023-06-08 09:00 | 2023-06-08 17:00 | 42 - Deploy software | 0% | Post Implementation Review | 45 - Distribute to team members | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
45 | 5.4.2 | Distribute to team members | Project Manager | 1 day | 2023-06-09 09:00 | 2023-06-09 17:00 | 44 - Document lessons learned | 0% | Post Implementation Review | 46 - Create software maintenance team | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog
46 | 5.4.3 | Create software maintenance team | Project Manager | 1 day | 2023-06-12 09:00 | 2023-06-12 17:00 | 45 - Distribute to team members | 0% | Post Implementation Review |  | 8 hours | 0 hours | 8 hours | No |  | Project Manager | Medium | Backlog